SECTION 01 3100

PROJECT MANAGEMENT AND COORDINATION

*****  The Design Professional shall include the following requirements as noted and complete this section with information for the specific project in coordination with PSFA Section 00 7200 - General Conditions*****

PART 1 - GENERAL

1.1	SUMMARY

A.	Section includes:

1.	General requirements for coordination of Work.

2.	Field engineering.

3.	Requirements for participation in and administration of:

a.	Pre-construction conference.

b.	Progress meetings.

c.	Pre-installation conferences.

4.	Progress schedule.

5.	[                            ]

B.	Related documents and sections:

1.	Document 00 0700 – General Conditions

a.	Paragraph 3.10 – Contractor’s Schedules, Logs, Meetings, and Reports

2.	Document 00 2113 - Instructions to Bidders:  Pre-Bid Conference.

3.	Section 01 1000  - Summary:  Work by others.

- Section 01 4000 – Quality Requirements:  Coordination with Owner’s project roof observer.

- Section 01 1500 – Temporary Facilities and Controls

1.2	SUBMITTALS

A.	Provide in accordance with Section 01 3300  - Submittal Procedures:

- Site mobilization plan (See Section 01 1500 and Paragraph 3.13 in Document 00 0700 – General Conditions)..

  - Submit for Owner’s approval prior to start of Work.

  - Update as necessary during progress of Work to adjust for changed conditions and as approved by Owner.

2.	Coordination drawings:

b.	Provide where coordination is critical for installation of components fabricated off site and where space is limited and maximum utilization of space is required.

c.	Show relationship and integration of components and construction entities, required installation sequence, dimensions, and tolerances.

B.	Staff assignment list and emergency contact information:

1.	Prior to Pre-Construction Conference, provide to Design Professional a list of Contractor's principal staff assignments for Project.  Indicate names, duties and responsibilities, addresses, emergency contact information and telephone numbers.  Include resume of proposed Project Superintendent showing prior experience as superintendent on projects of similar size and scope.  Naming more than one Project Superintendent to be in charge depending which is present at the site will not be acceptable.  Design Professional shall be informed in writing prior to any proposed change in Project Superintendent during the progress of the Work.  See also Paragraph 3.9 of the General Conditions.

2.	Distribute contact information and post in field office coordination.

1.3	GENERAL COORDINATION REQUIREMENTS (See Article 3 in General Conditions).

A.	Scheduling:  Coordinate scheduling, submittals and work of various specification sections to ensure efficient and orderly sequence of installation of interdependent construction elements.  Ensure that work of one specification section is not installed in such a manner as to limit, preclude, or restrict work of another section.

B.	Coordinate completion and clean up of work of separate specification sections in preparation for final inspection specified in Section 01 7700  - Closeout Procedures.

C.	After acceptance of Work, coordinate access to facility for required maintenance, monitoring, adjusting, and correcting deficiencies to manner to minimize disruption of Owner's activities.

D.	Coordinate with Owner regarding work of Owner’s forces and separate contractors.  Ensure coordination of such work with Project Schedule.

*****  Eliminate item below if no roofing work on project.*****

E.	Roofing Work Coordination with Owner and Roofing Consultant:	Contractor shall notify the PSFA Representative and Owner’s Roofing Consultant no later than 24 hours in advance regarding anticipated change in the roofing installation schedule due to prediction of bad weather or by other circumstances, including those directly caused by roof system installer, which will prevent roof system installation in accordance with the current Project Schedule.    Lack of adequate communication between Contractor and subcontractor regarding anticipated scheduling shall not relieve Contractor of this requirement.  Contractor shall be responsible for reimbursing to the Owner the related cost of Owner’s separate contractor services, including those of the Roofing Consultant if Contract roofing production rates are not met due to lack of compliance with these requirements.  See also Section 01 4000 – Quality Requirements.

*****  Eliminate item below if no Performance Assurance Contractor on project.*****

F.	HVAC & Control Performance Assurance Contractor (PAC) Coordination:	Contractor shall notify the PAC no later than 24 hours in advance regarding anticipated change in the HVAC & Controls installation schedule due to prediction of circumstances, including those directly caused by installer, which will prevent PAC tasks from being performed in accordance with the current Project Schedule.    Lack of adequate communication between Contractor and subcontractor regarding anticipated scheduling shall not relieve Contractor of this requirement.  Contractor shall be responsible for reimbursing to the Owner the related cost of Owner’s separate contractor services, including those of the PAC  due to lack of compliance with these requirements.  Examples of such expenses are separate contractor’s repeat trips and overtime made necessary by lack of Contractor’s compliance with this subparagraph.  See also Section 01 4000 – Quality Requirements.

1.4	FIELD ENGINEERING

A.	Existing control datum for field engineering is indicated on Drawings.

B.	Locate or establish survey control and reference points prior to starting site construction.  Protect points during construction and record locations with horizontal and vertical data on Project Record Documents in accordance with Section 01 7800  - Closeout Submittals.

C.	Prior to start of construction, verify location of control points and layout information on Drawings relative to property, setback, and easement lines.

D.	Provide competent field engineering services.  Establish elevations, lines, and levels utilizing recognized engineering survey practices.  Periodically verify layouts.

E.	Promptly replace dislocated control and reference points based on original survey control.

  - PROJECT COMMUNICATIONS SYSTEM (CIMS)

- Utilize PSFA – CIMS for project communications.  Refer to Document 00 7200  – General Conditions. Subparagraph 4.2.4.3.

- Arrange with Owner as necessary to obtain PSFA - CIMS training for Contractor’s principal staff on Project.

1.6 	PRE-CONSTRUCTION CONFERENCE

*****  Modify agenda based on project requirements.  Eliminate reference to PAC and/or roofing observer if not provided by Owner on project.*****

A.	Conference will be held after execution of the Agreement and prior to issuance of Notice To Proceed.  Time and location will be coordinated with Owner and Design Professional.  Meet at the site or other location convenient to all parties.

B.	Attendance:  Owner, school principal or other designated school representative, Design Professional, consultants, Contractor, and major subcontractors and suppliers.

C.	Agenda:

1.	Distribution of Contract Documents.

2.	Designation and description of roles of responsible personnel representing Owner, Contractor, and Design Professional.

3.	Status of permits and Notice to Proceed.

4.	Site mobilization plan, use of premises by Contractor and Owner, Owner's occupancy requirements, work hours, regular school schedule and special school schedule considerations.

5.	Construction schedule, work sequence, and delivery priorities.

6.	Weekly job meeting schedule.

7.	Owner’s right to salvage.

8.	Presentation and discussion of site mobilization plan specified in Section 01 50 00  - Temporary Facilities and Controls.

9.	Construction facilities, controls, and temporary utilities.

10.	Procedures for processing submittals, applications for payment, substitution requests, field decisions and communications, and contract modifications.

11.	PSFA - CIMS

12.	Wage rates.

13.	Security, Contractor’s use of keys, safety, first aid, and housekeeping.

14.	Behavior of work force on school site.

15.	Procedures for spotting of utility lines [by Owner’s forces].

16.	Procedures for maintaining project record documents.

17.	Requirements for start up of equipment.

18.	Testing and inspection procedures.

19.	Introduce Owner’s separate contractors and consultants, [including PAC and roofing observer].

20.	Inspection and acceptance of equipment put into service during construction.

21.	Contract closeout procedures.

- Emergency contact information.

23.	Other pertinent items.

1.7	PROGRESS MEETINGS

A.	Refer to Document 00 7200 General Conditions – Paragraph 3.10 for requirements.

.

B. Progress Meetings shall include review of Owner’s separate contractor issues including the PAC Design Issues Log and Installation Issues Log with actions required, those individuals assigned for resolution, and expected resolution date.

1.8	PRE-INSTALLATION CONFERENCES

*****  Each section requiring pre-installation conference should list items to be covered at conference and cross reference to this section for meeting procedures.  If pre-installation conferences are not required, delete this article.  *****

A.	When required by an individual specification section, convene a pre-installation conference at site.

B.	Require attendance of entities directly concerned with item of work.

C.	Notify Design Professional 4 days in advance of meeting.

D.	Prepare agenda and preside at conference.  Record minutes, and distribute copies within 3 days to participants and Design Professional.

E.	At meeting, review conditions of installation, preparation and installation procedures, and coordination with related work.

1.9	PROGRESS SCHEDULE

A.	See Paragraph 3.10 in the General Conditions for requirements.

*****  Coordinate with Owner’s roofing consultant regarding required roofing production rates and ensure that these are included within the Contract Documents prior to bidding.  Eliminate this item if no roofing on Project.*****

- [ Indicate complete sequence of roofing activity in compliance with roofing production rates required by Contract.]

*****  Coordinate with Owner’s Performance Assurance Contactor (PAC) regarding required Contractor scheduling requirements and ensure that these are included within the Contract Documents prior to bidding.  Eliminate this item if no PAC on Project.*****

- [ Indicate complete sequence of HVAC and controls installation activity as separate line items and testing in compliance with requirements of Owner’s Performance Assurance Contractor (PAC).  Itemize each category of subcontracted work, especially those related to PAC activities and illustrate separately on the Project Schedule. Consult with PAC to determine milestones, critical paths and time requirements to complete Test and Balance and performance verification testing prior to Owner’s occupancy of Project and insert in Project Schedule.  See Subparagraph 1.3-F regarding Contractor’s responsibility for maintaining PAC involvement in Project Schedule.]

PART 2 - PRODUCTS

2.1	EQUIPMENT

A.	Verify utility requirements and characteristics of equipment are compatible with facility utilities.  Coordinate work of various specification sections having interdependent requirements for installing, connecting to, and placing in service such equipment.

PART 3 - EXECUTION

3.1	COORDINATION WITH INSTALLED CONSTRUCTION

A.	Cutting and patching of installed construction shall be accomplished in accordance with Section 01 7000  - Execution Requirements.

END OF SECTION